## A
International Union of Crystallography
| SPECIAL ISSUE PRODUCTION SCHEDULE |  |  |  | 2013-11-01
| Proposed issue title: | PLEASE TYPE THE ISSUE TITLE HERE
| Expected number of articles: | PLEASE PROVIDE AN ESTIMATE OF THE EXPECTED NUMBER OF AUTHORS
| Expected number of pages: | PLEASE PROVIDE AN ESTIMATE OF THE EXPECTED NUMBER OF JOURNAL PAGES
| Guest Editors: | PLEASE PROVIDE THE NAMES AND CONTACT DETAILS OF THE PROPOSED GUEST EDITORS
| Suggested publication date: | 2014-11-01 |  | PLEASE TYPE THE REQUIRED PUBLICATION DATE HERE
Lead Times (in working days)
-260 | Provision of the scope of the issue and names of potential contributors* |  |  |  |  | 2013-10-23
*50% more authors should be proposed than the size of the issue
-255 | Agreement of scope and authors by Editor-in Chief* |  |  |  |  | 2013-10-30
*The EiC would aim to suggest inviting about 30% more authors than the minimal viable special issue
-250 | Authors invited by Guest Editors (confirmation asked for within two weeks) |  |  |  |  | 2013-11-06
-240 | Confirmation deadline |  |  |  |  | 2013-11-20
-230 | Confirmed authors submit co-author names and 300 word synopsis to Guest Editors |  |  |  |  | 2013-12-04
-120 | Deadline for submission |  |  |  |  | 2014-05-15
-45 | Reviews complete/deadline for uploading of accepted paper |  |  |  |  | 2014-09-01
-22 | Proofs out/deadline for submission of front material (cover image, preface/editorial, running order of papers etc.) |  |  |  |  | 2014-10-02
| Online |  |  |  |  | 2014-11-01
| Any other comments on the special issue: |  | PLEASE PROVIDE ADDITIONAL COMMENTS HERE. FOR EXAMPLE, IF THERE MIGHT BE FUNDING AVAILABLE TO MAKE ARTICLES OPEN ACCESS, PLEASE SPECIFY THE DETAILS HERE.
BANK HOL
2013-12-25
2013-12-26
2014-01-01
2014-04-18
2014-04-21
2014-05-06
2014-05-26
2014-08-25
2014-12-25
2014-12-26
2015-01-01
2015-04-03
2015-04-06
2015-05-04
2015-05-25
2015-08-31
2015-12-25
2015-12-28